## Slide 1: ARM MTE Study
Grange Nagy
Juan Trevino
Estimated Total Hours: 8-10 per person for solely
the project

## Slide 2: Plans (Past Week)
Explore MTE tag distribution gaming
Read into the code online
  Work on documenting the code
  Read the bootloader
Explore dumping tags
  Want to see a snapshot of the tags of a live system
Reproduce Project Zero blog tests

## Slide 3: What Actually Happened
Work completed: most
Explore MTE tag distribution gaming WIP
  Max of 6 tags guessed in a row
Read into the code online
  Work on documenting the code
  Extract the 2nd stage bootloader
    Done
Explore dumping tags
  Easiest way to examine the distribution of tags in the live system is via core dumps
    Issue: Using gcore() too much causes the system to become unstable
    Solution: Patience probably, ulimit -c unlimited
  Can also use ptrace(), iterating over /proc/<pid>/smaps segments marked with “mt” (memory tag)
Reproduction: Done

## Slide 4: Plans (Next Week)
Finish getting the system tag distribution at runtime
Continue documenting the code, begin writing the paper
Explore X3 and A715 cores
Continue working on exploring gaming the distribution